## Guidelines (hidden)
Business Readiness Checklist (BRC)
Purpose
BRC is a decision support process to ensure readiness at each project phase. It provides a structured approach to measure if the project and business are ready to move to the next stage of the project lifecycle. Ultimately it is used to determine if the project is ready to go live.
Governance
The Project Manager is responsible for preparing and tabling the BRC; typically the Project Manager may delegate this responsibility to the Deployment Manager.
The J2FM Operational Working Committee are accountable for reviewing and approving the BRC, and approving progression to the next project stage or go live.
Objectives
Defines all conditions to be met for Go-Live
Ensures all critical tasks are monitored on a regular basis
Identifies critical activities and conditions at risk, and ensure mitigation actions are put in place to resolve them
Provides the project team with the information to enable an informed GO/NO GO decision
Manages stakeholder expectations on progress
Provides auditable evidence
Checkpoints
Business Readiness checkpoints have been based on the J2FM Block Plan Milestones to ensure alignment:
Checkpoint 1 | Confirm approval of Blueprint Exit Reports (FDWC & FEWC) and Build Exit Reports (FEWC), and readiness to start testing
Checkpoint 1.5 | Confirm successful completion of the Component Integration Testing phase, and readiness to move into System/E2E testing
Checkpoint 2 | Confirm successful completion of the System, E2E Test Phase, and readiness to Start Security & Performance Testing, UVT
Checkpoint 3 | Confirm successful completion of the Security & Performance Phase & UVT and readiness to move into Final Preparation.
Checkpoint 4 | Confirm planned Final Preparation tasks are successfully completed, and readiness to move into Cutover.
Checkpoint 5 | Confirm successful completion of Cutover processes for Go-live.
BRC Structure
The BRC process consists of a series of conditions that need to comply with specific approval criteria to ensure readiness for go-live.
Platform | All aspects related to required physical infrastructure, systems (infrastructure & applications) including network performance & decommissioning.
People | People related, including training, communications and organisation structures.
Process | Management of issues, support structures, 3rd party contracts
Policy | Legal reporting requirements, as well as tax and audit issues.
Conditions
The PM and key project stakeholders need to review each condition and assess it's relevance to the project. If irrelevant, amend the status to closed and enter a comment to that effect. Where necessary conditions should be reviewed and a decision made on the relevant entry for that condition. i.e agree an owner; agree whether the status needs to be green for go live etc.
All conditions have a project owner (for reporting & tracking purposes).
Responsibility for task completion lies with Tactical Release Team.
All conditions have been assigned a minimal go-live requirement. This will be used to assess the criticality of this condition for go-live (R/A/G).
Some conditions will be measured post-go-live.
There are 2 key indicators for each condition:
– Status NOW: Measuring the completeness of a condition by its due checkpoint (R/A/G).
– Status GO-LIVE: Measuring the ‘forecast’ completeness of a condition by go-live (R/A/G).
If a project will not have an impact on a specific condition or component, these can be omitted from the checklist.
Status Indicators
COMPLETE - complete / ready now
GREEN - complete / ready now
LIGHT GREEN - complete – on track – well within due date – however not fully signed off yet
AMBER - not complete – on track – however on critical path - not fully signed off yet
LIGHT RED - not complete – on critical path – not signed off – and needs focus to ensure that we meet the deadline
RED - not complete – on critical path – not signed off – and it is forecast that we will not be ready in time and will almost certainly lead to us missing the go-live date – this will be the most serious situation and will lead us to conclude that we will have to postpone the go-live

## Auto (Graphs)
Inland Revenue - [INITIATIVE NAME] |  |  | DATE
Production Entry Readiness Dashboard
Customer Readiness | Business Readiness | Go-Live Readiness
Are our Customer reday to receive the change? | Is the business ready to operate and support the solution? | Final measures @ Go-Live
Solution & Technology Readiness
Is the solution ready and are transition and early life sypport plans in place?
Readiness Area: By Status
Automatically generated.

## Production Entry
Fill this in to obtain your 5 assessment dates
[9 empty] | Target Go/No Go Date: |  |  |  |  | dd/mm/yy
[9 empty] | C | Complete / ready now
[9 empty] | G | Complete – on track – well within due date – however not fully signed off yet
[9 empty] | LG | Not Complete – On track – needs active management to be completed by due date – not fully signed off yet
[9 empty] | LA | Not Complete - On track - but may start to impact critical path criteria - not fully signed off yet
[9 empty] | A | Not Complete – On track – however on critical path - not fully signed off yet
[9 empty] | LR | Not Complete – On critical path – not signed off – and needs focus to ensure that we meet the deadline
Release Readiness Assessment : [INSERT INITIATIVE NAME] | [8 empty] | R | Not Complete – On critical path – not signed off – and it is forecast that we will not be ready in time and it will almost certainly lead to us missing the Go-live date.
[9 empty] | C |  |  |  |  | after each checkpoint add C to checkpoint / remove from prior check
| Components Identifies the specific parts/sections to be monitored | Ref # | Condition Identifies the condition relevant to each component/element | Metrics & Targets | Project interpretation of the Metric & Target (exceptions only) | Target Date | Condition Owner | Function | #VALUE! | #VALUE! | #VALUE! | #VALUE! | dd/mm/yy | Comments / Progress Update this column when the criteria is reviewed and/or at each checkpoint | Issues arising from this Checkpoint (Document any issues arising from the Checkpoint Review that need to be resolved) | Actions to close the issues (Document the actions required to resolve the open issues and obtain required go live status / sign-off) | Action Owner (Person responsible for ensuring the action is completed)
CUSTOMER READINESS | External Communications & Readiness | 1.01 | Customer Communication Plan - plan developed, reviewed and approved | Plan developed and approved by [approval forum] | <<document the project specific interpretation of the check if it is not directly applicable to this project, but is close enough to be useful to assess>> | dd/mm/yy |  | Cross Agency Partner | R
|  | 1.02 | Customer Communications - customers with specific change impacts have been communicated to according to plan | Customer Communications plan executed; * Pre-migration comms complete * Post-migration comms ready to be executed No material unresolved negative supplier feedback |  | dd/mm/yy |  | Project | LR
|  | 1.03 | Supplier Communication Plan - plan developed, reviewed and approved | Plan developed and approved by [approval forum] |  | dd/mm/yy |  | Project | A
|  | 1.04 | Supplier Communications - suppliers with specific change impacts have been communicated to according to plan | Supplier Communications plan executed; * Pre-migration comms complete * Post-migration comms ready to be executed No material unresolved negative supplier feedback |  | dd/mm/yy |  | Project | LA
|  | 1.05 | Intermediaries (e.g. Tax Agents) Communications - intermediaries with specific change impacts have been communicated to according to plan | Intermediaries Communications plan executed; * Pre-migration comms complete * Post-migration comms ready to be executed No material unresolved negative supplier feedback |  | dd/mm/yy |  | Project | LG
|  | 1.06 | Other Government Agencies - ready |  |  | dd/mm/yy |  | Project | G
|  | 1.07 | Marketing, Media & Communications - ready | Marketing & Communications prepared to support any Public Relations activity required pre and post go live. Public Relations response plan in place and feedback received |  | dd/mm/yy |  | Project | C
|  | 1.08 | Intermediaries and third parties - ready | IR's assessment of the readiness of dependent intermediaries and third parties |  | dd/mm/yy |  | Business | NA
BUSINESS READINESS | Org Readiness | 2.01 | Organisational Alignment - structures in place for day one and roles provisioned | Day one business structure has been developed with all appropriate roles filled and accountabilities defined. - approved changes to organisation structure -updated and new role definitions approved - resources in place for all roles |  | dd/mm/yy |  | Business
|  | 2.02 | Resource Levels - business unit resourcing is at agreed levels required to support Solution Implementation | Workforce impacts of solution measured and accepted. All resources in place as per workforce requirements |  | dd/mm/yy |  | Business
|  | 2.03 | Business Processes - future state processes and policy defined, documented and approved | All future state process and policy documented and approved. All business processes proven in system. Business processes updated for changes from User Acceptance Testing |  | dd/mm/yy |  | Business
|  | 2.04 | Business reporting - ready | Operational reporting is ready |  | dd/mm/yy |  | Business
|  | 2.05 | Business Change Impacts - assessed and business readiness (change management) approach documented, reviewed and approved | All future state process and policy documented and approved. All business processes proven in system. Business processes updated for changes from User Acceptance Testing |  | dd/mm/yy |  | Business
| Training | 2.06 | Training Content - critical content developed before go live | All Content and Training modules and user QRGs documented before Go-Live |  | dd/mm/yy |  | Business
|  | 2.07 | Staff trained - courses offered/attendance in accordance with training needs analysis and training schedule | Training effective and users confident to use the new system All identified people trained (or agreed target %'age) Re-training and catch-up training plan developed Training effectiveness feedback measurement target achieved |  | dd/mm/yy |  | Business
| Internal Communications | 2.08 | Staff communications - People directly or indirectly affected by the release (including senior stakeholders) have been notified in accordance with the internal communications plan | All staff have been notified in accordance with the internal communications plan. Senior stakeholders communicated to according to plan |  | dd/mm/yy |  | Project
| Service Design | 2.09 | Service Design - Service Design Package documented before go-live (also refer to IT Support Model) | Service Design Package approved and communicated to responsible staff |  | dd/mm/yy |  | Business
|  | 2.1 | Operational Support - knowledge Transferred | 100% of Operational Support Guide/Manual/Work Instructions Documented Operations Support team has accepted knowledge transfer |  | dd/mm/yy |  | Business
|  | 2.11 | Business Continuity - plan has been updated or documented prior to go-live | Responsible staff have been notified of BCP plan (including updates) |  | dd/mm/yy |  | Business
|  | 2.12 | Disaster Recovery - has DR procedures been created/updated and has DR test in the production environment been completed/planned. (for new systems or systems changed, that has DR capability) | IR Service Continuity Manager has signed off: 1. the new or amended DR procedure 2. A DR test completion report or DR test plan |  | dd/mm/yy |  | Business
| Policy and Legislation | 2.13 | Legislative change requirements established | Enabling legislation passed. |  | dd/mm/yy |  | Business
|  | 2.14 | Policy Decisions | All outstanding Policy questions answered. |  | dd/mm/yy |  | Business
|  | 2.15 | Ministerial Decisions | Any required Ministerial decision required to support implementation under authority delegated to MoR. |  | dd/mm/yy |  | Business
|  | 2.16 | Legal Documentation | Terms and Conditions and any Agreement defined and agreed for inclusion in service design. |  | dd/mm/yy |  | Business
| Benefits Realisation | 2.17 | KPI - Framework to measure business performance impacts endorsed | KPI Framework shared and approved with business owners with reporting in place |  | dd/mm/yy |  | Project
| Business Transition | 2.18 | Business Transition - strategy and approach documented, reviewed and approved | Business Transition Strategy/Approach approved and communicated |  | dd/mm/yy |  | Project
|  | 2.19 | Business Transition - detailed plan defining how business unit users will be transitioned to the new processes | Business Transition plan approved and communicated. |  | dd/mm/yy |  | Business
|  | 2.2 | Business Transition Communications - transition communications plan in place and resources to execute communication plan available | Transition Communication plan documented and approved Resources in place for preparation of communication during business transition events Checkpoint meetings scheduled and accepted. Dial in numbers in place Communication templates/standards and processes approved. Emergency communication processes in place |  | dd/mm/yy |  | Project
SOLUTION & TECHNOLOGY READINESS | Deployment | 3.01 | Deployment Approach, Strategy and Plan - documented, reviewed and approved | Deployment strategy, approach and plan approved by [approval forum] |  | dd/mm/yy |  | Project
|  | 3.02 | Decommissioning - Legacy Systems targeted for decommissioning are in Read-Only / Restricted Access mode - | In-scope systems have been frozen, all data migration / go-live database snapshots have been taken and stored in the target location(s) and systems have been placed into read only / hibernation mode with user access updated as per the defined requirements - Sign-off on decommissioning check lists |  | dd/mm/yy |  | Project
|  | 3.03 | Dependencies - all dependencies on other projects have been identified and included with deployment, cut-over and contingency plans | Dependencies identified in planning documents |  | dd/mm/yy |  | Project
|  | 3.04 | Integrated Deployment Plan - detailed plan & schedule to cover all activity for the cutover period documented, reviewed and approved | Detailed deployment plan (including schedule and business and technical cutover activities) prepared, approved and communicated. Cutover plan successfully rehearsed |  | dd/mm/yy |  | Project
|  | 3.05 | In-flight Strategy and Delivery Approach - In-flight design documented, agreed and communicated. Cutover processes and reporting developed. | Design completed and approved inflight process successfully tested in Dress Rehearsal. Exit criteria achieved |  | dd/mm/yy |  | Project
|  | 3.06 | Deployment Communications - plan in place and resources to execute communication plan available | Deployment and Cutover Communication plan prepared and approved. Resources in place for preparation of communication during cutover event Communication templates in place. Emergency communication processes in place |  | dd/mm/yy |  | Project
|  | 3.07 | Deployment Resource Planning - all resource assigned to cut-over tasks are available | Technical/Project, business resource & 3rd party resource in place for Dress Rehearsal No key gaps in resource demand v supply Rehearsals and Cutover |  | dd/mm/yy |  | Project
|  | 3.08 | Deployment Readiness - Dress Rehearsals executed successfully | Dress Rehearsal run to schedule and an acceptable level of quality. Exit criteria achieved |  | dd/mm/yy
|  | 3.09 | Deployment Readiness - Outage Window | Outage window (including contingency for rollback) communicated and agreed with business and ICT. Outage communications executed |  | dd/mm/yy |  | Project
|  | 3.1 | Cutover readiness - Business validation of key transactions (Production Implementation Testing - PIV) | Detailed PIV plan prepared, approved and communicated. PIV data identified. PIV scripts ready PVT Exit criteria agreed: - 100% of PIV scenarios identified in the cutover plan have been validated with no severity 1 or 2 issues outstanding - Accepted work arounds for all P3 defects Business resource to validate key transactions available (during cutover) |  | dd/mm/yy |  | Project
|  | 3.11 | Cutover Rollback Strategy & Plan - process defined, agreed and tested | Roll back plan documented, reviewed and approved Back up and restore processes previously proven in production or pre-production |  | dd/mm/yy |  | Project
|  | 3.12 | Cutover logistics - documented, reviewed and approved | Logistics requirements defined and arrangements in place, including; - Travel booked and accommodation booked for all identified users - Security arrangements in place where required - Contact details for all Cutover resources - Food and refreshments available for cutover team |  | dd/mm/yy |  | Project
|  | 3.13 | Change Records - have been created and ready for approval in ServiceNow | Endorsement from Change and Release Manager that change/ release records are ready for approval |  | dd/mm/yy |  | Project
| Data | 3.14 | Data Migration Successful - % of applicable entities are migrated and achieve status for key functionality | Trial Conversion test exit criteria achieved for entry to cutover event; % of entities migrated successfully (break out for key entities) |  | dd/mm/yy |  | Project
|  | 3.15 | Volume of manual migration ( post go-live) - Approach defined and resourcing agreed for entities that will have to be migrated manually, This includes records impacted by data cleansing not completed prior to go-live. | Days to remediate post go live Number of manual migrations |  | dd/mm/yy |  | Project
|  | 3.16 | Business & finance reconciliation successful - Reconciliation and verification results from final Dress Rehearsal within agreed tolerance levels | Business and financial metrics TBC |  | dd/mm/yy |  | Project
|  | 3.17 | Migration Defects Addressed Prior to go-live - all critical, and major migration defects addressed prior to go-live. Moderate and minor defects significant reduced. | # of defects # of impacted entities and/or processes |  | dd/mm/yy |  | Project
| Support and Stabilisation | 3.18 | Early life support model - documented, reviewed and approved | ELS support model that will meet the business needs and is approved by [approval forum] |  | dd/mm/yy |  | Project
|  | 3.19 | Early life support (ELS)processes trained and resources in place - ELS processes that are to be owned by the ELS support team are defined, tested and resourced. | ELS support model in place, including; - Processes documented and approved. - Resources in place to execute processes. - Measurement reporting in place. - Level 1 and level 2 Incident reporting tools in place and tested. - Triage processes defined and agreed. - Business users communicated to. According to plan |  | dd/mm/yy |  | Project
|  | 3.2 | Business Support Structure - in place for impacted business teams. | Impacted teams identified. Teams and sites identified and communicated to the Business. Support people identified and secured. |  | dd/mm/yy |  | Project
|  | 3.21 | Business Support Logistics - plan complete | Logistics requirements defined and arrangements in place, including: - Travel booked and accommodation booked for all identified support staff - Security arrangements in place where required - Contact details for all resources - Hours of support confirmed |  | dd/mm/yy |  | Project
|  | 3.22 | Early Life Support - processes tested and resources in place. | Processes documented and approved Trial run of processes completed Resources in place to execute processes reporting framework established and measurement reporting in place. |  | dd/mm/yy |  | Project
|  | 3.23 | Emergency Release - Emergency/Contingency releases secured for release of high priority defects during ELS | Date of emergency releases confirmed Resources to manage release identified and in place |  | dd/mm/yy |  | Project
|  | 3.24 | Commercial Support Arrangements - documented and agreed with third party suppliers | Contractual arrangements signed off |  | dd/mm/yy |  | Project
|  | 3.25 | Early Life Support exit criteria - agreed with Operations | Exit criteria defined and agreed with Operations |  | dd/mm/yy |  | Project
| Solution Quality | 3.26 | Test Success - documentation review and approval of the test exit report | Execution completed and Exit Reports signed off; - No Sev 1 & 2 defects (per Test Strategy severity definition). Plans, comms and resolution dates agreed for Sev 3 & 4 defects. |  | dd/mm/yy |  | Project
|  | 3.27 | Report Development - all reports required for go live are developed. | Go Live reports developed in time for go live or agreement in place for alternative outcome. - No Sev 1 & 2 defects on go live reports (per Test Strategy severity definition). Plans, comms and resolution dates agreed for Sev 3 & 4's |  | dd/mm/yy |  | Project
|  | 3.28 | The end-to-end infrastructure and technical landscape is ready in all respects - Required infrastructure & environments are built to specification, fully connected and operating within the defined parameters. | IT Test Exit Report signed off OAT Test exit report signed off Solution Architecture Document (As-Built) signed off - No Sev 1 & 2 defects on go live reports (per Test Strategy severity definition). Plans, comms and resolution dates agreed for Sev 3 & 4's |  | dd/mm/yy |  | Project
|  | 3.29 | The end-to-end solution performance is acceptable - Solution is operating within defined parameters and has proven Disaster Recovery (DR) processes across solution | OAT Test exit report signed off DR (Warm and Cold) Test Exit Report signed off Solution Architecture Document (As-Built) signed off - No Sev 1 & 2 defects on go live reports (per Test Strategy severity definition). Plans, comms and resolution dates agreed for Sev 3 & 4's |  | dd/mm/yy |  | Project
| Risk Assessment | 3.3 | Final Risk Assessment - Completion of Inland Revenue Security Certification and Accreditation. | Completion of Inland Revenue Security Risk Accreditation. Acceptance of Risk Assessment by the appropriate [approval forum] |  | dd/mm/yy |  | Project
APPROVALS | Approvals | 4.01 | Deployment Readiness - Steering Committee approval | Documented approval in EWC Committee minutes |  | dd/mm/yy |  | Project
|  | 4.02 | Deployment Readiness - ECRB Approval | Documented approval in Enterprise Change Release Board (ECRB) Minutes |  | dd/mm/yy |  | Project
|  | 4.03 | Technical Validation - CRB Approval | Documented approval in Change Release Board (CRB) Minutes |  | dd/mm/yy |  | Project
Note on G11: Target Date for Readiness to be assessed as complete
Note on H11: Person responsible for ensuring the condition is ready at the appropriate Gate / Go Live
Note on I11: Indicates whether the Project Team or the Business have the responsibility to achieve the required condition / status

## ADMINOnly
PLEASE DO NOT CHANGE OR UPDATE ANYTHING IN THIS SHEET - Please contact the admin owner
Column1 | C | G | LG | LA | A | LR | R | NA | Column2
Customer Readiness | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
Business Readiness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution & Technology Readiness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8
| C | G | LG | LA | A | LR | R | NA
External Communications | bar: C to NA
Org Readiness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Internal Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Benefits Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy & Legislation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Business Transition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deployment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support & Stabilisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution Quality | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approvals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | bar: C to NA
Customer Readiness | C: External Communications; G: 1.01; LG: R
Customer Readiness | C: External Communications; G: 1.02; LG: LR
Customer Readiness | C: External Communications; G: 1.03; LG: A
Customer Readiness | C: External Communications; G: 1.04; LG: LA
Customer Readiness | C: External Communications; G: 1.05; LG: LG
Customer Readiness | C: External Communications; G: 1.06; LG: G
Customer Readiness | C: External Communications; G: 1.07; LG: C
Customer Readiness | C: External Communications; G: 1.08; LG: NA
Business Readiness | C: Org Readiness; G: 2.01; LG: 0
Business Readiness | C: Org Readiness; G: 2.02; LG: 0
Business Readiness | C: Org Readiness; G: 2.03; LG: 0
Business Readiness | C: Org Readiness; G: 2.04; LG: 0
Business Readiness | C: Org Readiness; G: 2.05; LG: 0
Business Readiness | C: Training; G: 2.06; LG: 0
Business Readiness | C: Training; G: 2.07; LG: 0
Business Readiness | C: Internal Communications; G: 2.08; LG: 0
Business Readiness | C: Service Design; G: 2.09; LG: 0
Business Readiness | C: Service Design; G: 2.1; LG: 0
Business Readiness | C: Service Design; G: 2.11; LG: 0
Business Readiness | C: Service Design; G: 2.12; LG: 0
Business Readiness | C: Policy & Legislation; G: 2.13; LG: 0
Business Readiness | C: Policy & Legislation; G: 2.14; LG: 0
Business Readiness | C: Policy & Legislation; G: 2.15; LG: 0
Business Readiness | C: Policy & Legislation; G: 2.16; LG: 0
Business Readiness | C: Benefits Realisation; G: 2.17; LG: 0
Business Readiness | C: Business Transition; G: 2.18; LG: 0
Business Readiness | C: Business Transition; G: 2.19; LG: 0
Business Readiness | C: Business Transition; G: 2.2; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.01; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.02; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.03; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.04; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.05; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.06; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.07; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.08; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.09; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.1; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.11; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.12; LG: 0
Solution & Technology Readiness | C: Deployment; G: 3.13; LG: 0
Solution & Technology Readiness | C: Data; G: 3.14; LG: 0
Solution & Technology Readiness | C: Data; G: 3.15; LG: 0
Solution & Technology Readiness | C: Data; G: 3.16; LG: 0
Solution & Technology Readiness | C: Data; G: 3.17; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.18; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.19; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.2; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.21; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.22; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.23; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.24; LG: 0
Solution & Technology Readiness | C: Support & Stabilisation; G: 3.25; LG: 0
Solution & Technology Readiness | C: Solution Quality; G: 3.26; LG: 0
Solution & Technology Readiness | C: Solution Quality; G: 3.27; LG: 0
Solution & Technology Readiness | C: Solution Quality; G: 3.28; LG: 0
Solution & Technology Readiness | C: Solution Quality; G: 3.29; LG: 0
Business Readiness | C: Risk Assessment; G: 3.3; LG: 0
Business Readiness | C: Approvals; G: 4.01; LG: 0
Business Readiness | C: Approvals; G: 4.02; LG: 0
Business Readiness | C: Approvals; G: 4.03; LG: 0